## Slide 1
PROGRAMME POSITIONING
A command centre, not another programme deck.
The operating hub is organised around one simple flow: select the date → see the agenda → open the material → know what must exist by the end of the session.
WHAT THIS CHANGES
No hunting through folders.
No guessing what happens next.
No separate “facilitator manual” to interpret.
Every scheduled touchpoint has a Day Pack containing the exact agenda, owner, preparation, expected outputs and direct material links.
Problem → Build → Deploy
4 graduates
20 Aug intake
2 Oct showcase
Success = visible, useful outputs

## Slide 2
CALENDAR & ROADMAP
The full programme on one page.
Preparation is completed before the intake; the remaining six weeks move from controlled practice into real MRANTI work, validation, QA and showcase.
01
13–19 Aug
Readiness
Challenges, sponsors, tools & room ready
02
20–21 Aug
Activation Lab
Problem → live prototype
03
24–28 Aug
Division Discovery
Real problem scoped with sponsor
04
1–4 Sep
Build Sprint 1
First sponsor-usable version
05
8–11 Sep
Validate
Internal user testing
06
14–18 Sep
Build Sprint 2
Evidence + usability + story
07
21–25 Sep
Final Build & QA
Deployment and handover ready
08
28 Sep–2 Oct
Showcase & Handover
Management showcase + next step
INTAKE
Thu · 20 Aug
OPERATING RHYTHM
Sponsor demos + clinics
FINAL SHOWCASE
Fri · 2 Oct
MEASURE OF PROGRESS
Working links + sponsor usefulness

## Slide 3
HOW THE TEAM USES IT
One date = one complete Day Pack.
A teammate does not need to understand the entire programme to run their part. They open the date and everything required for that session is already there.
01
SELECT DATE
Choose the scheduled touchpoint from the programme calendar.
02
READ AGENDA
See timing, session purpose, owner and expected output.
03
OPEN MATERIAL
Launch the exact worksheet, prompt, guide or checklist for that day.
04
CLOSE THE OUTPUT
Know what must exist before the session can be considered complete.
Example · 20 Aug Activation Day → exact 09:00–16:30 agenda → facilitator guide + graduate workbook + case study + prompt pack + GitHub guide → live prototype by end of day

## Slide 4
20 AUGUST
Activation Day: problem to live prototype.
This is the first major Day Pack and the teaching model the graduates will repeat in their real division projects.
09:00
Positioning
Problem note
09:20
Problem discovery
Problem statement
10:10
AI requirements
Requirement brief
11:00
Build web output
Local prototype
14:00
GitHub Pages
Live link
15:00
Mini showcase
Feedback backlog
16:00
Division next steps
Workstream assignment
MATERIALS IN THE DAY PACK
Facilitator Guide
Graduate Workbook
Activation Day Case Study
AI Prompt Pack
GitHub Pages Quick Guide
Starter Prototype

## Slide 5
DECISION POINTS
What needs to be locked before the graduates arrive.
The Command Centre is already structured. The remaining management input is deliberately small and operational.
01
4 challenge areas
Choose real, bounded problems that can show a useful first version quickly.
02
4 sponsors / reviewers
Each graduate needs one person who can validate the business usefulness every week.
03
Data & access boundary
Confirm what information can be used and what must remain internal.
04
Prototype delivery approval
Confirm GitHub Pages can be used for non-sensitive working prototypes.
05
Final showcase audience
Confirm who should attend on 2 October and what follow-up decisions are expected.
Once these are confirmed, the team can operate from the Command Centre date-by-date.